## Overview
BCP / Disaster Recovery Plan
Critical Services · RTO/RPO · Dependencies · Recovery Steps · Test Results
DOCUMENT CONTROL
Organization Name:
Department / Team:
Document Owner:
Author / Prepared By:
Version: | 1.0
Status: | Draft
Date Created:
Last Reviewed:
Next Review Date:
Classification: | Confidential
Distribution: | Internal - do not distribute externally without approval
ℹ Version history and approval sign-off are maintained in the 'Version & Approval' tab.
© SecureSlate ¦ getsecureslate.com ¦ Template v1.0 ¦ Provided for informational purposes. Consult qualified professionals for compliance advice.

## Version & Approval
VERSION HISTORY
Version | Date | Description of Changes | Changed By | Reviewed By | Approved By
1.0 |  | Initial release
APPROVAL SIGN-OFF
Role | Name (Print) | Signature |  | Comments
Prepared By
Reviewed By (Security Team)
Reviewed By (Legal / DPO)
Approved By (CISO / Security Lead)
Approved By (Executive Sponsor)
This document is controlled. Any printed copy is uncontrolled unless stamped 'CONTROLLED COPY'. Refer to getsecureslate.com for the latest version.

## Critical Services
CRITICAL SERVICES REGISTER
# | Service / System | Business Function | Priority Tier | RTO Target | RPO Target | MTPD | Service Owner | Recovery Team | Backup Location | Dependencies
1 | Customer-Facing Web Application | Primary product delivery | Tier 1 | 4 hours | 1 hour | 24 hours | CTO | Engineering | AWS us-west-2 | Auth service, DB, CDN
2 | Authentication Service | User login and access | Tier 1 | 1 hour | 15 mins | 4 hours | IT Manager | IT Ops | AWS us-east-1 | User DB, MFA provider
3 | Customer Database | Core data store | Tier 1 | 2 hours | 15 mins | 8 hours | CISO | IT Ops + DBA | Automated daily snapshot | Web app, Auth service
4 | Payment Processing | Revenue operations | Tier 1 | 2 hours | 30 mins | 4 hours | Finance | IT Ops | Third-party provider | PSP, Finance system
5 | Internal Email (Microsoft 365) | Employee communication | Tier 2 | 8 hours | 4 hours | 48 hours | IT Manager | IT Ops | Microsoft cloud | Active Directory
6 | HR System (BambooHR) | Payroll and HR operations | Tier 2 | 24 hours | 4 hours | 72 hours | HR Manager | HR + IT | Vendor hosted | Employee directory
7 | Development Environment | Product development | Tier 3 | 48 hours | 24 hours | 7 days | CTO | Engineering | GitHub | CI/CD pipeline
RTO = Recovery Time Objective ¦ RPO = Recovery Point Objective ¦ MTPD = Maximum Tolerable Period of Disruption

## Dependencies Map
DEPENDENCY REGISTER
# | Service / System | Dependency Type | Dependency Name | Provider | Criticality | Single Point of Failure? | Mitigation
1 | Customer Web App | Cloud Infrastructure | AWS us-east-1 | Amazon Web Services | Critical | No (multi-region) | Failover to us-west-2
2 | Auth Service | Identity Provider | Okta | Okta | Critical | Yes | Fallback to local auth pending
3 | Payment Processing | Payment Gateway | Stripe | Stripe | Critical | Yes | Backup PSP agreement in place
4 | All Systems | Domain Name | Route53 DNS | Amazon | High | No (redundant) | Secondary DNS provider
5 | All Systems | Internet Connectivity | ISP Circuit | Vodafone | High | No (dual ISP) | Failover to 4G backup
6 | Corporate Systems | Email | Microsoft 365 | Microsoft | High | No (cloud-hosted) | Vendor SLA 99.9%
7 | Dev Environment | Source Control | GitHub | GitHub | Medium | No (cloud-hosted) | Mirrored to Bitbucket
8 | All Systems | Monitoring | Datadog | Datadog | High | Yes | Fallback alerting via PagerDuty

## Recovery Procedures
RECOVERY PROCEDURES
# | Service / System | Phase | Recovery Steps | Dependencies | Owner | Est. Time
1 | Auth Service | 1. Assess | Check health dashboard; confirm outage scope; notify IC | Monitoring system | IT Ops | 15 mins
2 | Auth Service | 2. Activate | Activate BCP; engage recovery team; open war room | IR team | IC | 15 mins
3 | Auth Service | 3. Failover | Switch DNS to standby region; validate auth traffic routing | Route53, standby cluster | IT Ops | 30 mins
4 | Auth Service | 4. Validate | Run smoke tests on login flows; confirm user access restored | QA team | Engineering | 30 mins
5 | Customer Database | 1. Assess | Check RDS status; estimate data loss window vs last backup | AWS RDS, CloudWatch | DBA | 15 mins
6 | Customer Database | 2. Restore | Restore from latest snapshot to standby instance | AWS RDS snapshot | DBA + IT Ops | 60–90 mins
7 | Customer Database | 3. Repoint | Update connection strings; flush connection pools | App config, deploy pipeline | Engineering | 30 mins
8 | Customer Database | 4. Validate | Run data integrity checks; confirm RPO met | Data validation scripts | DBA | 30 mins

## DR Test Results
DR TEST RESULTS LOG
# | Test Date | Test Type | Scope / Systems | RTO Target | Actual RTO | RPO Target | Actual RPO | Result | Lessons / Actions
1 | 2026-01-15 | Tabletop Exercise | Auth + DB failover | 1 hour | N/A | 15 mins | N/A | Pass | Updated runbook step 3 — DNS TTL needed lowering
2 | 2025-09-10 | Partial Failover | Customer DB | 2 hours | 1h 45m | 15 mins | 12 mins | Pass | Met targets; document restore sequence improvement
3 | 2025-03-22 | Full DR Simulation | All Tier 1 services | 4 hours | 5h 20m | 1 hour | 55 mins | Fail | RTO exceeded — added standby replica to fix