## Overview
ISO 27001 Risk Treatment Plan
Treatment options · Annex A controls · owners and due dates · residual risk · acceptance (clause 6.1.3)
DOCUMENT CONTROL
Organization Name:
Department / Team:
Document Owner:
Author / Prepared By:
Version: | 1.0
Status: | Draft
Date Created:
Last Reviewed:
Next Review Date:
Classification: | Confidential
Distribution: | Internal. Do not distribute externally without approval.
HOW TO USE THIS WORKBOOK
1. Settings | Set your scoring thresholds and risk appetite (the highest residual score you accept without escalation).
2. Risk Treatment Plan | One row per risk, so the Dashboard counts stay accurate. If a risk needs several actions, list them in Treatment action and use the last due date. Copy risks from your risk register, choose a treatment option and Annex A control, then track owner, dates and progress. Scores, levels, timeline status and the appetite check calculate automatically.
3. Annex A Controls | Reference list of all 93 ISO/IEC 27001:2022 controls; it feeds the control dropdown. Keep your SoA consistent with the controls chosen here.
4. Dashboard | Inherent vs residual levels, treatment options, overdue actions, risks above appetite and unaccepted residual risk. Bring it to management review (clause 9.3).
Owner acceptance | Clause 6.1.3 f) requires risk owners to approve the plan and accept residual risk. Record the acceptance and date per row.
Example rows | Rows R-001 to R-004 are examples. Overwrite or delete them. Formulas are ready for 300 rows.
Version history and approval sign-off are kept on the Version & Approval tab. Fill in document control before your audit.
© SecureSlate ¦ getsecureslate.com ¦ Template v1.0 ¦ Provided as is, not legal advice.

## Dashboard
RISK TREATMENT DASHBOARD
Updates automatically from the other tabs. Do not type in this sheet.
Key figures | Value |  | Inherent risk heat map
Risks in the plan | 4 |  | Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
Average completion | 65% |  | 5 | 0 | 0 | 0 | 0 | 0
Overdue actions | 0 |  | 4 | 0 | 0 | 0 | 0 | 1
Due soon | 0 |  | 3 | 0 | 0 | 0 | 1 | 1
Residual risk above appetite | 1 |  | 2 | 0 | 1 | 0 | 0 | 0
Residual risk not yet accepted by owner | 2 |  | 1 | 0 | 0 | 0 | 0 | 0
Inherent level | Count | Share | Cell colours use the default thresholds. Counts update as you score risks.
Critical | 1 | 25%
High | 2 | 50% | Residual risk heat map
Medium | 0 | 0% | Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
Low | 1 | 25% | 5 | 0 | 0 | 0 | 0 | 0
Total | 4 |  | 4 | 0 | 0 | 0 | 0 | 0
|  |  | 3 | 0 | 0 | 0 | 0 | 0
Residual level | Count | Share | 2 | 0 | 1 | 2 | 0 | 1
Critical | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0
High | 1 | 25%
Medium | 2 | 50% | Cell colours use the default thresholds. Counts update as you score risks.
Low | 1 | 25%
Total | 4
Treatment option | Count | Share
Modify | 2 | 50%
Avoid | 0 | 0%
Share | 1 | 25%
Retain | 1 | 25%
Total | 4
Timeline | Count | Share
Overdue | 0 | 0%
Due soon | 0 | 0%
On track | 2 | 50%
No due date | 0 | 0%
Completed | 2 | 50%
Cancelled | 0 | 0%
Total | 4

## Version & Approval
VERSION HISTORY
Version | Date | Description of Changes | Changed By | Reviewed By | Approved By
1.0 |  | Initial release
APPROVAL SIGN-OFF
Role | Name (Print) | Signature | Date
Prepared By
Reviewed By (Security Team)
Approved By (CISO / Security Lead)
Approved By (Executive Sponsor)

## Settings
SETTINGS
Change the values in column C to fit your organization. Every formula in the workbook reads from here.
Risk scoring and appetite | Value | Notes
Critical when score is at least | 17 | Score = likelihood x impact (1 to 25).
High when score is at least | 10
Medium when score is at least | 5 | Anything lower is Low.
Risk appetite: highest acceptable residual score | 9 | Residual scores above this are flagged for escalation to top management.
Due soon window (days) | 14
Likelihood scale | Score | Meaning
Rare | 1 | Less than once in 5 years
Unlikely | 2 | Once in 2 to 5 years
Possible | 3 | About once a year
Likely | 4 | Several times a year
Almost certain | 5 | Monthly or more often
Impact scale | Score | Meaning
Negligible | 1 | No customer or patient effect, trivial cost
Minor | 2 | Limited internal disruption, small cost
Moderate | 3 | Some customers affected or a small data exposure
Major | 4 | Breach of sensitive data or outage affecting many customers
Severe | 5 | Regulatory action, large breach or threat to the business

## Risk Treatment Plan
ISO 27001 RISK TREATMENT PLAN
Risk ID | Risk description | Asset / process | Risk owner | Inherent likelihood (1-5) | Inherent impact (1-5) | Inherent score | Inherent level | Treatment option | Treatment action | Primary Annex A control | Other controls | Action owner | Start date | Due date | Status | % complete | Days remaining | Timeline | Residual likelihood (1-5) | Residual impact (1-5) | Residual score | Residual level | Within appetite | Residual risk accepted by owner | Acceptance date | Notes
R-001 | Unauthorized access to production data through stolen admin credentials | Production database | CTO | 4 | 5 | 20 | Critical | Modify | Enforce phishing-resistant MFA for all admin accounts | 8.5 Secure authentication | 5.17, 8.2 | IT Lead | 2026-11-01 | 2026-12-15 | In progress | 60% | 42 | On track | 2 | 5 | 10 | High | No: escalate
R-002 | Ransomware encrypts file shares and backups | Backups | Head of Engineering | 3 | 5 | 15 | High | Modify | Immutable, off-account backups with quarterly restore tests | 8.13 Information backup | 5.30 | SRE Lead | 2026-10-15 | 2026-11-20 | Not started | 0% | 17 | On track | 2 | 3 | 6 | Medium | Yes
R-003 | Vendor breach exposes customer data | Email marketing vendor | COO | 3 | 4 | 12 | High | Share | Add security clauses and breach notice SLA; cyber insurance | 5.20 Addressing information security within supplier agreements | 5.19, 5.21 | Legal | 2026-09-01 | 2026-10-31 | Completed | 100% |  | Completed | 2 | 3 | 6 | Medium | Yes | Yes | 2026-11-02
R-004 | Office break-in and theft of devices | Office | COO | 2 | 2 | 4 | Low | Retain | Accept: devices are encrypted and data is cloud-hosted | 7.1 Physical security perimeters | 8.1 | COO |  |  | Completed | 100% |  | Completed | 2 | 2 | 4 | Low | Yes | Yes | 2026-11-02
Formulas:
Days remaining = IF(OR([Due date]="",[Status]="Completed",[Status]="Cancelled"),"",[Due date]-TODAY())
Timeline = IF([Risk description]="","",IF([Status]="Completed","Completed",IF([Status]="Cancelled","Cancelled",IF([Due date]="","No due date",IF([Due date]<TODAY(),"Overdue",IF([Due date]-TODAY()<=DUE_SOON_DAYS,"Due soon","On track"))))))

## Annex A Controls
ISO/IEC 27001:2022 ANNEX A CONTROLS
Control (ID and name) | Theme | Name
5.1 Policies for information security | Organisational | Policies for information security
5.2 Information security roles and responsibilities | Organisational | Information security roles and responsibilities
5.3 Segregation of duties | Organisational | Segregation of duties
5.4 Management responsibilities | Organisational | Management responsibilities
5.5 Contact with authorities | Organisational | Contact with authorities
5.6 Contact with special interest groups | Organisational | Contact with special interest groups
5.7 Threat intelligence | Organisational | Threat intelligence
5.8 Information security in project management | Organisational | Information security in project management
5.9 Inventory of information and other associated assets | Organisational | Inventory of information and other associated assets
5.10 Acceptable use of information and other associated assets | Organisational | Acceptable use of information and other associated assets
5.11 Return of assets | Organisational | Return of assets
5.12 Classification of information | Organisational | Classification of information
5.13 Labelling of information | Organisational | Labelling of information
5.14 Information transfer | Organisational | Information transfer
5.15 Access control | Organisational | Access control
5.16 Identity management | Organisational | Identity management
5.17 Authentication information | Organisational | Authentication information
5.18 Access rights | Organisational | Access rights
5.19 Information security in supplier relationships | Organisational | Information security in supplier relationships
5.20 Addressing information security within supplier agreements | Organisational | Addressing information security within supplier agreements
5.21 Managing information security in the ICT supply chain | Organisational | Managing information security in the ICT supply chain
5.22 Monitoring, review and change management of supplier services | Organisational | Monitoring, review and change management of supplier services
5.23 Information security for use of cloud services | Organisational | Information security for use of cloud services
5.24 Information security incident management planning and preparation | Organisational | Information security incident management planning and preparation
5.25 Assessment and decision on information security events | Organisational | Assessment and decision on information security events
5.26 Response to information security incidents | Organisational | Response to information security incidents
5.27 Learning from information security incidents | Organisational | Learning from information security incidents
5.28 Collection of evidence | Organisational | Collection of evidence
5.29 Information security during disruption | Organisational | Information security during disruption
5.30 ICT readiness for business continuity | Organisational | ICT readiness for business continuity
5.31 Legal, statutory, regulatory and contractual requirements | Organisational | Legal, statutory, regulatory and contractual requirements
5.32 Intellectual property rights | Organisational | Intellectual property rights
5.33 Protection of records | Organisational | Protection of records
5.34 Privacy and protection of PII | Organisational | Privacy and protection of PII
5.35 Independent review of information security | Organisational | Independent review of information security
5.36 Compliance with policies, rules and standards for information security | Organisational | Compliance with policies, rules and standards for information security
5.37 Documented operating procedures | Organisational | Documented operating procedures
6.1 Screening | People | Screening
6.2 Terms and conditions of employment | People | Terms and conditions of employment
6.3 Information security awareness, education and training | People | Information security awareness, education and training
6.4 Disciplinary process | People | Disciplinary process
6.5 Responsibilities after termination or change of employment | People | Responsibilities after termination or change of employment
6.6 Confidentiality or non-disclosure agreements | People | Confidentiality or non-disclosure agreements
6.7 Remote working | People | Remote working
6.8 Information security event reporting | People | Information security event reporting
7.1 Physical security perimeters | Physical | Physical security perimeters
7.2 Physical entry | Physical | Physical entry
7.3 Securing offices, rooms and facilities | Physical | Securing offices, rooms and facilities
7.4 Physical security monitoring | Physical | Physical security monitoring
7.5 Protecting against physical and environmental threats | Physical | Protecting against physical and environmental threats
7.6 Working in secure areas | Physical | Working in secure areas
7.7 Clear desk and clear screen | Physical | Clear desk and clear screen
7.8 Equipment siting and protection | Physical | Equipment siting and protection
7.9 Security of assets off-premises | Physical | Security of assets off-premises
7.10 Storage media | Physical | Storage media
7.11 Supporting utilities | Physical | Supporting utilities
7.12 Cabling security | Physical | Cabling security
7.13 Equipment maintenance | Physical | Equipment maintenance
7.14 Secure disposal or re-use of equipment | Physical | Secure disposal or re-use of equipment
8.1 User end point devices | Technological | User end point devices
8.2 Privileged access rights | Technological | Privileged access rights
8.3 Information access restriction | Technological | Information access restriction
8.4 Access to source code | Technological | Access to source code
8.5 Secure authentication | Technological | Secure authentication
8.6 Capacity management | Technological | Capacity management
8.7 Protection against malware | Technological | Protection against malware
8.8 Management of technical vulnerabilities | Technological | Management of technical vulnerabilities
8.9 Configuration management | Technological | Configuration management
8.10 Information deletion | Technological | Information deletion
8.11 Data masking | Technological | Data masking
8.12 Data leakage prevention | Technological | Data leakage prevention
8.13 Information backup | Technological | Information backup
8.14 Redundancy of information processing facilities | Technological | Redundancy of information processing facilities
8.15 Logging | Technological | Logging
8.16 Monitoring activities | Technological | Monitoring activities
8.17 Clock synchronisation | Technological | Clock synchronisation
8.18 Use of privileged utility programs | Technological | Use of privileged utility programs
8.19 Installation of software on operational systems | Technological | Installation of software on operational systems
8.20 Networks security | Technological | Networks security
8.21 Security of network services | Technological | Security of network services
8.22 Segregation of networks | Technological | Segregation of networks
8.23 Web filtering | Technological | Web filtering
8.24 Use of cryptography | Technological | Use of cryptography
8.25 Secure development life cycle | Technological | Secure development life cycle
8.26 Application security requirements | Technological | Application security requirements
8.27 Secure system architecture and engineering principles | Technological | Secure system architecture and engineering principles
8.28 Secure coding | Technological | Secure coding
8.29 Security testing in development and acceptance | Technological | Security testing in development and acceptance
8.30 Outsourced development | Technological | Outsourced development
8.31 Separation of development, test and production environments | Technological | Separation of development, test and production environments
8.32 Change management | Technological | Change management
8.33 Test information | Technological | Test information
8.34 Protection of information systems during audit testing | Technological | Protection of information systems during audit testing